## Shortlist
Teaming partner shortlist
Buyer | U.S. Fish and Wildlife Service |  |  | As of | 2026-09-15
Pursuit | Bitter Lake NWR survey
Prime | GovTribe, Inc. · UEI EDJBUPNLCCL5 |  | Solicitation | 140FC126R0018
Due | 2026-09-24 | 5:00 PM EDT |  | Submittal | SF330
GovTribe’s identity is real; scenario assumptions and past performance are illustrative. Real opportunity and candidate companies.
2 shortlist · 2 research further · 0 exclude
Next steps and candidate inputs
ID | Company / UEI | Proposed role | Recommendation | Why | Main conditions | Candidate | Next action | Required checks | Source ID | Main issue | Input check
C01 | Dewberry Engineers Inc. UEI K3WDSCEDY1V5 | Lead airborne topobathymetric collection. | Shortlist | Green-laser capability disclosure and a NOAA mapping award warrant contact. | Aircraft slot and licensed team are unconfirmed. 0 failed; 7 unresolved | C01 Dewberry Engineers Inc. UEI K3WDSCEDY1V5 | Ask for a sensor/crew plan, licensed staff and one recent evaluated project. | 0 failed; 7 unresolved | V01 | Aircraft slot and licensed team are unconfirmed.
C02 | NV5 Geospatial, Inc. UEI EMJEL3XM6A87 | Alternative lead for airborne collection and processing. | Shortlist | NOAA documents bathymetric work; a recent mapping award warrants contact. | Recent evaluated project and proposed team are unconfirmed. 0 failed; 6 unresolved | C02 NV5 Geospatial, Inc. UEI EMJEL3XM6A87 | Request a recent project, intended contracting entity and November–February availability. | 0 failed; 6 unresolved | V02 | Recent evaluated project and proposed team are unconfirmed.
C03 | Woolpert, Inc. UEI LD8UDJB9JLU1 | Possible LiDAR/imagery collection partner. | Research further | NOAA LiDAR/imagery award is relevant; bathymetric evidence is still missing. | Airborne bathymetric method and staff are unconfirmed. 0 failed; 8 unresolved | C03 Woolpert, Inc. UEI LD8UDJB9JLU1 | Request a bathymetric method and reference before adding to the contact shortlist. | 0 failed; 8 unresolved | V03 | Airborne bathymetric method and staff are unconfirmed.
C04 | Surdex Corporation UEI KHTMVK6LLH11 | Possible topographic LiDAR and imagery support. | Research further | Interior LiDAR/imagery award suggests a supporting role. | Bathymetric capability and workshare are unconfirmed. 0 failed; 8 unresolved | C04 Surdex Corporation UEI KHTMVK6LLH11 | Confirm interest in a supporting package and whether bathymetric capability is available. | 0 failed; 8 unresolved | V04 | Bathymetric capability and workshare are unconfirmed.

## Teaming Needs
Teaming needs
Prime capabilities |  | Illustrative GovTribe capabilities: project coordination and GIS integration only. No aircraft, bathymetric sensor, field crew or named New Mexico licensed manager is assumed.
Teaming structure |  | Proposed prime/subcontractor team; no partners committed.
Requirements come from the buyer. Gaps describe the prime profile; B01 supports the example assumptions.
ID | Need | Priority | Buyer requirement | Prime gap | Citation | Input check | Source ID | Location
N01 | Airborne bathymetric LiDAR | Required | Airborne bathymetric collection using the October 2025 bathymetric specification. Ground-based bathymetry cannot replace it. | Prime has no bathymetric sensor or flight crew. | S04 pp2,8–9; RFI 01,20,24,25 |  | S04 | pp2,8–9; RFI 01,20,24,25
N02 | Topographic LiDAR and imagery | Required | Topographic collection at 8 points/m² or better, plus 3-inch, four-band orthophotography. | Prime has no aircraft or image acquisition equipment. | S02 pp5–6,10–11 |  | S02 | pp5–6,10–11
N03 | Ground control and field survey | Required | Six primary control points in the Middle/South tracts and detailed surveys of 20 water-control structures. Visible utilities are sufficient. | Prime has no field crew or named New Mexico survey professional. | S04 pp2–3,9; RFI 04,06,25 |  | S04 | pp2–3,9; RFI 04,06,25
N04 | LiDAR processing and delivery | Required | Deliver hydro-flattened and topobathymetric DEMs and an ESRI breakline geodatabase, with the specified quality checks. | Prime can integrate GIS outputs; specialist bathymetric processing and validation are not assumed. | S04 pp4–5,9; RFI 09,23 |  | S04 | pp4–5,9; RFI 09,23

## Capability Match
Capability match
Assess the stated public evidence, not readiness to perform. A supported capability still needs the pursuit-specific confirmations in the last column.
ID | Candidate ID | Need ID | Status | Evidence assessment | Citation | What we need to get | Input check | Source ID | Location | Priority
M11 | C01 | N01 | Pass | Dewberry reports a green-laser sensor for topographic and bathymetric mapping. Allocation to this legal entity and pursuit is unconfirmed. | T01 Company announcement | Provide the proposed airborne method, sensor and a relevant project. |  | T01 | Company announcement | Required
M12 | C01 | N02 | Pass | Public award scope includes LiDAR and imagery. This supports relevant work scope, not compliance with every Bitter Lake specification. | W01 Raw award description | Confirm the specified point density, four-band imagery and proposed equipment. |  | W01 | Raw award description | Required
M13 | C01 | N03 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Identify the field crew, New Mexico license holders and survey deliverables. |  |  |  | Required
M14 | C01 | N04 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Provide a deliverable sample, QA approach and the responsible processing team. |  |  |  | Required
M21 | C02 | N01 | Pass | NOAA records NV5 collection and processing of coastal topobathymetric data in 2019–2020. Current staff and entity continuity need confirmation. | T02 Abstract; supplemental information | Provide the proposed airborne method, sensor and a relevant project. |  | T02 | Abstract; supplemental information | Required
M22 | C02 | N02 | Pass | Public award scope includes LiDAR and imagery. This supports relevant work scope, not compliance with every Bitter Lake specification. | W02 Raw award description | Confirm the specified point density, four-band imagery and proposed equipment. |  | W02 | Raw award description | Required
M23 | C02 | N03 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Identify the field crew, New Mexico license holders and survey deliverables. |  |  |  | Required
M24 | C02 | N04 | Pass | NOAA records NV5 collection and processing of coastal topobathymetric data in 2019–2020. Current staff and entity continuity need confirmation. | T02 Abstract; supplemental information | Provide a deliverable sample, QA approach and the responsible processing team. |  | T02 | Abstract; supplemental information | Required
M31 | C03 | N01 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Provide the proposed airborne method, sensor and a relevant project. |  |  |  | Required
M32 | C03 | N02 | Pass | Public award scope includes LiDAR and imagery. This supports relevant work scope, not compliance with every Bitter Lake specification. | W03 Raw award description | Confirm the specified point density, four-band imagery and proposed equipment. |  | W03 | Raw award description | Required
M33 | C03 | N03 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Identify the field crew, New Mexico license holders and survey deliverables. |  |  |  | Required
M34 | C03 | N04 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Provide a deliverable sample, QA approach and the responsible processing team. |  |  |  | Required
M41 | C04 | N01 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Provide the proposed airborne method, sensor and a relevant project. |  |  |  | Required
M42 | C04 | N02 | Pass | Public award scope includes LiDAR and imagery. This supports relevant work scope, not compliance with every Bitter Lake specification. | W04 Raw award description | Confirm the specified point density, four-band imagery and proposed equipment. |  | W04 | Raw award description | Required
M43 | C04 | N03 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Identify the field crew, New Mexico license holders and survey deliverables. |  |  |  | Required
M44 | C04 | N04 | Unresolved | The inspected public records do not establish this capability for the proposed team. |  | Provide a deliverable sample, QA approach and the responsible processing team. |  |  |  | Required

## Relevant Work
Relevant work
Award dates and scheduled completion are distinct from project collection dates. Public awards do not establish quality, completed work or partner availability.
ID | Candidate | Award / project | Customer | Actual role | Dates | Work reference | Need ID | Relevance | Limitations | Source ID | Location | Start date | End date | Input check
R01 | Dewberry Engineers Inc. UEI K3WDSCEDY1V5 | 1305M225D0016-1305M226F0404 | NOAA / National Geodetic Survey | Named prime awardee | Aug 31, 2026 to Apr 19, 2029 | C01 | N02 | Awarded LiDAR, imagery and shoreline mapping in Washington. | Scheduled completion only. No inspected evaluation, accepted deliverables or proof of available staff. | W01 | Award fields; raw description | 2026-08-31 | 2029-04-19
R02 | NV5 Geospatial, Inc. UEI EMJEL3XM6A87 | 1305M225D0017-1305M226F0396 | NOAA / National Geodetic Survey | Named prime awardee | Aug 21, 2026 to Jun 30, 2028 | C02 | N02 | Awarded LiDAR, imagery and shoreline mapping in Washington. | Scheduled completion only. No inspected evaluation, accepted deliverables or proof of available staff. | W02 | Award fields; raw description | 2026-08-21 | 2028-06-30
R03 | Woolpert, Inc. UEI LD8UDJB9JLU1 | 1305M225D0018-1305M226F0340 | NOAA / National Geodetic Survey | Named prime awardee | Jul 27, 2026 to Sep 29, 2028 | C03 | N02 | Awarded LiDAR, imagery and shoreline mapping in Washington. | Scheduled completion only. No inspected evaluation, accepted deliverables or proof of available staff. | W03 | Award fields; raw description | 2026-07-27 | 2028-09-29
R04 | Surdex Corporation UEI KHTMVK6LLH11 | 47QTCA18D00J5-140S0326F0009 | Interior / Surface Mining Reclamation and Enforcement | Named prime awardee | Sep 10, 2026 to Jan 31, 2027 | C04 | N02 | Awarded LiDAR and aerial imagery services. | Scheduled completion only. No inspected evaluation, accepted deliverables or proof of available staff. | W04 | Award fields; raw description | 2026-09-10 | 2027-01-31
R05 | NV5 Geospatial, Inc. UEI EMJEL3XM6A87 | NOAA: 2019–2020 coastal topobathymetric LiDAR | NOAA / National Geodetic Survey | Named data collector; contract role not established | Nov 26, 2019 to Aug 25, 2020 | C02 | N01 | NOAA identifies NV5 Geospatial as the collector of coastal topobathymetric data. | Collection dates, not award dates. Outside the three-year experience window; no current registrant or staff continuity proven. | T02 | Abstract; item identification | 2019-11-26 | 2020-08-25

## Checks & Actions
Checks & actions
TEAM applies to every candidate. Dates are internal planning targets. A Pass needs recorded confirmation; citation of a buyer requirement alone is insufficient.
ID | Candidate ID | Check | Required | Status | Action | Due date | Timing | Check ID | Confirmation / evidence | Citation | Source ID | Location | Input check
K1L | C01 | New Mexico licensed personnel | Yes | Unresolved | Request named manager/alternate and relevant New Mexico registrations; confirm their role and commitment. | 2026-09-18 | Upcoming | K1L / C01 |  | S04 pp3–4,7; RFI 07,18 | S04 | pp3–4,7; RFI 07,18
K1A | C01 | Flight window and teaming interest | Yes | Unresolved | Confirm interest, sensor and crew availability for Nov 2026–Feb 2027, and coordination within two weeks of refuge clearing. | 2026-09-17 | Upcoming | K1A / C01 |  | S03 p2 criteria 6–7; S04 pp6–8 | S03 | p2 criteria 6–7; S04 pp6–8
K1P | C01 | Recent evaluated project | Yes | Unresolved | Obtain at least one recent relevant project for this firm with client, purpose, dates and evaluation. Current awards are insufficient. | 2026-09-18 | Upcoming | K1P / C01 |  | S04 pp5–6; RFI 13–14 | S04 | pp5–6; RFI 13–14
K2L | C02 | New Mexico licensed personnel | Yes | Unresolved | Request named manager/alternate and relevant New Mexico registrations; confirm their role and commitment. | 2026-09-18 | Upcoming | K2L / C02 |  | S04 pp3–4,7; RFI 07,18 | S04 | pp3–4,7; RFI 07,18
K2A | C02 | Flight window and teaming interest | Yes | Unresolved | Confirm interest, sensor and crew availability for Nov 2026–Feb 2027, and coordination within two weeks of refuge clearing. | 2026-09-17 | Upcoming | K2A / C02 |  | S03 p2 criteria 6–7; S04 pp6–8 | S03 | p2 criteria 6–7; S04 pp6–8
K2P | C02 | Recent evaluated project | Yes | Unresolved | Obtain at least one recent relevant project for this firm with client, purpose, dates and evaluation. Current awards are insufficient. | 2026-09-18 | Upcoming | K2P / C02 |  | S04 pp5–6; RFI 13–14 | S04 | pp5–6; RFI 13–14
K3L | C03 | New Mexico licensed personnel | Yes | Unresolved | Request named manager/alternate and relevant New Mexico registrations; confirm their role and commitment. | 2026-09-18 | Upcoming | K3L / C03 |  | S04 pp3–4,7; RFI 07,18 | S04 | pp3–4,7; RFI 07,18
K3A | C03 | Flight window and teaming interest | Yes | Unresolved | Confirm interest, sensor and crew availability for Nov 2026–Feb 2027, and coordination within two weeks of refuge clearing. | 2026-09-17 | Upcoming | K3A / C03 |  | S03 p2 criteria 6–7; S04 pp6–8 | S03 | p2 criteria 6–7; S04 pp6–8
K3P | C03 | Recent evaluated project | Yes | Unresolved | Obtain at least one recent relevant project for this firm with client, purpose, dates and evaluation. Current awards are insufficient. | 2026-09-18 | Upcoming | K3P / C03 |  | S04 pp5–6; RFI 13–14 | S04 | pp5–6; RFI 13–14
K4L | C04 | New Mexico licensed personnel | Yes | Unresolved | Request named manager/alternate and relevant New Mexico registrations; confirm their role and commitment. | 2026-09-18 | Upcoming | K4L / C04 |  | S04 pp3–4,7; RFI 07,18 | S04 | pp3–4,7; RFI 07,18
K4A | C04 | Flight window and teaming interest | Yes | Unresolved | Confirm interest, sensor and crew availability for Nov 2026–Feb 2027, and coordination within two weeks of refuge clearing. | 2026-09-17 | Upcoming | K4A / C04 |  | S03 p2 criteria 6–7; S04 pp6–8 | S03 | p2 criteria 6–7; S04 pp6–8
K4P | C04 | Recent evaluated project | Yes | Unresolved | Obtain at least one recent relevant project for this firm with client, purpose, dates and evaluation. Current awards are insufficient. | 2026-09-18 | Upcoming | K4P / C04 |  | S04 pp5–6; RFI 13–14 | S04 | pp5–6; RFI 13–14
KTP | TEAM | Prime eligibility and division of work | Yes | Unresolved | Validate prime small-business eligibility and a compliant prime/sub work split before choosing the team; do not rely on the fictional profile. | 2026-09-18 | Upcoming | KTP / TEAM |  | S01 Set-aside; validate applicable terms in base solicitation | S01 | Set-aside; validate applicable terms in base solicitation
KTR | TEAM | Complete SF330 team and schedule | Yes | Unresolved | Agree tasks, licensed staff and schedule; compile at least three recent evaluated references, including one for each proposed firm. Submit SF330 by Sep 24, 5 PM EDT. | 2026-09-21 | Upcoming | KTR / TEAM |  | S04 pp5–7,10; S03 p2 criterion 6 | S04 | pp5–7,10; S03 p2 criterion 6

## Sources
Sources
Blue cells are editable inputs; gray cells calculate. Expand grouped columns on other tabs to edit source IDs.
Source dates describe the document or record update. Retrieval dates show when this research was frozen.
ID | Title | Type | Source date | Retrieved | Limitation | URL | UEI | Source ID | Input check
S01 | NM BITTER LAKE NWR AERIAL IMAGING | GovTribe record | 2026-08-13 | 2026-09-15 | Discovery and identity. Use amendments for due date and conditions; AI summary misstates the site visit. | https://govtribe.com/opportunity/federal-contract-opportunity/nm-bitter-lake-nwr-aerial-imaging-140fc126r0018 |  | S01
S02 | Bitter Lake performance work statement | Government document |  | 2026-09-15 | PDF pages used. Read with amendment 0003; document issue date not relied on. | https://govtribe.com/file/government-file/performance-work-statement-bitter-lake-lidar-final-dot-pdf |  | S02
S03 | SF330 ranking criteria | Government document |  | 2026-09-15 | Amendment 0003 clarifies references, licensure and schedule. No price proposal requested. | https://govtribe.com/file/government-file/ranking-criteria-140fc126r0018-dot-pdf |  | S03
S04 | Amendment 0003 — questions and answers | Government document |  | 2026-09-15 | Controlling clarifications; p10 confirms Sep 24, 2026 at 5 PM EDT. Header date not used as posting date. | https://govtribe.com/file/government-file/140fc126r0018-sol-140fc126r0018-amd-0003-dot-pdf |  | S04
V01 | Dewberry Engineers Inc. | GovTribe record | 2025-12-16 | 2026-09-15 | Exact registrant. Public registration data do not establish interest, available staff or eligibility for this role. | https://govtribe.com/vendors/dewberry-engineers-inc-dot-4djx0 | K3WDSCEDY1V5 | V01
W01 | 1305M225D0016-1305M226F0404 | GovTribe record | 2026-08-31 | 2026-09-15 | Recent award; scheduled end date. No completed deliverables, evaluation or available staff verified. | https://govtribe.com/award/federal-contract-award/delivery-order-1305m225d0016-1305m226f0404 |  | W01
V02 | NV5 Geospatial, Inc. | GovTribe record | 2026-09-07 | 2026-09-15 | Exact registrant. Public registration data do not establish interest, available staff or eligibility for this role. | https://govtribe.com/vendors/quantum-spatial-inc-dot-9r590 | EMJEL3XM6A87 | V02
W02 | 1305M225D0017-1305M226F0396 | GovTribe record | 2026-08-21 | 2026-09-15 | Recent award; scheduled end date. No completed deliverables, evaluation or available staff verified. | https://govtribe.com/award/federal-contract-award/delivery-order-1305m225d0017-1305m226f0396 |  | W02
V03 | Woolpert, Inc. | GovTribe record | 2026-03-19 | 2026-09-15 | Exact registrant. Public registration data do not establish interest, available staff or eligibility for this role. | https://govtribe.com/vendors/woolpert-inc-dot-0kr30 | LD8UDJB9JLU1 | V03
W03 | 1305M225D0018-1305M226F0340 | GovTribe record | 2026-07-27 | 2026-09-15 | Recent award; scheduled end date. No completed deliverables, evaluation or available staff verified. | https://govtribe.com/award/federal-contract-award/delivery-order-1305m225d0018-1305m226f0340 |  | W03
V04 | Surdex Corporation | GovTribe record | 2025-11-26 | 2026-09-15 | Exact registrant. Public registration data do not establish interest, available staff or eligibility for this role. | https://govtribe.com/vendors/surdex-corporation-8g253 | KHTMVK6LLH11 | V04
W04 | 47QTCA18D00J5-140S0326F0009 | GovTribe record | 2026-09-10 | 2026-09-15 | Recent award; scheduled end date. No completed deliverables, evaluation or available staff verified. | https://govtribe.com/award/federal-contract-award/delivery-order-47qtca18d00j5-140s0326f0009 |  | W04
T01 | Dewberry: second CZMIL SuperNova sensor | Company disclosure | 2024-07-23 | 2026-09-15 | Company disclosure. Confirm legal entity, sensor allocation and crew. No commitment inferred. | https://www.dewberry.com/insights-news/article/2024/07/23/dewberry-acquires-second-czmil-supernova-sensor |  | T01
T02 | NOAA: 2019–2020 coastal topobathymetric LiDAR | Government dataset | 2026-08-19 | 2026-09-15 | 2019–2020 collection; metadata updated 2026. Not a recent reference. Confirm current entity and staff. | https://www.fisheries.noaa.gov/inport/item/66707 |  | T02
B01 | Illustrative prime capability profile | Internal assumption | 2026-09-15 | 2026-09-15 | Illustrative GovTribe capability assumptions: coordination and GIS integration only. No aircraft, field crew or licensed manager assumed. |  |  | B01